## Risk Calculation Sheet
AMERICAN EXPRESS — EMV CHIP TRANSITION RISK ASSESSMENT
LIKELIHOOD (Probability of Occurrence) |  |  |  | IMPACT OF RISK (Inherent Risk — before controls)
Label | Score |  | Label | Score
Very Unlikely | 1 |  | Very Low | 1
Somewhat Unlikely | 3 |  | Somewhat Low | 2
50-50 Possibility | 5 |  | Moderate | 4
Somewhat Likely | 7 |  | Somewhat High | 6
Very Likely | 9 |  | High | 8
|  |  | Extremely High | 9
THRESHOLD DEFINITIONS (Maximum Possible Score = 81)
HIGH | Score 54 – 81
MEDIUM | Score 27 – 53
LOW | Score 1 – 26
FOUR RISK TYPES — IMPACT SCORES
Impact Level | Score |  | Financial | Operational | Competitive | Reputational
Very Low | 1
Somewhat Low | 2
Moderate | 4
Somewhat High | 6 |  |  | ✔ Selected (Score=6)
High | 8 |  | ✔ Selected (Score=8) |  | ✔ Selected (Score=8) | ✔ Selected (Score=8)
Extremely High | 9
RISK SCORE SUMMARY
Risk # | OKA | Likelihood Label | Likelihood Score | Impact Label | Impact Score | Risk Score (L × I) | Priority | probability | Expected Impact
R-001 | Financial | Somewhat Likely | 7 | High | 8 | 56 | HIGH | 77.78% | 69.14%
R-002 | Operational | Somewhat Likely | 7 | Somewhat High | 6 | 42 | MEDIUM | 77.78% | 51.85%
R-003 | Competitive | Very Likely | 9 | High | 8 | 72 | HIGH | 100% | 88.89%
R-004 | Reputational | 50-50 Possibility | 5 | High | 8 | 40 | MEDIUM | 55.56% | 49.38%
R-005 | Legall/Compliance | Somewhat Likely | 7 | Somewhat High | 6 | 42 | MEDIUM | 77.78% | 51.85%
R-006 | Operational | Somewhat Likely | 7 | Somewhat High | 6 | 42 | MEDIUM | 77.78% | 51.85%
References Jalilvand, A., & Moorthy, S. (2023). Triangulating risk profile and risk assessment. Journal of Risk and Financial Management, 16(11), 473. https://doi.org/10.3390/jrfm16110473 Pape, C. (2025). Visa, Mastercard settle merchant suit for nearly $200M. American Banker. https://www.americanbanker.com/payments/news/visa-mastercard-settle-merchant-suit-for-nearly-200m Fitzgerald, K. (2016). Why EMV failed to meet terminal makers' expectations.American Banker. https://www.americanbanker.com/payments/news/why-emv-failed-to-meet-terminal-makers-expectations

## Risk Heat Map
AMERICAN EXPRESS EMV TRANSITION — RISK HEAT MAP
■ HIGH (54–81) | ■ MEDIUM (27–53) | ■ LOW (1–26)
IMPACT ↓ / LIKELIHOOD → | Very Unlikely (1) | Somewhat Unlikely (3) | 50-50 Possibility (5) | Somewhat Likely (7) | Very Likely (9)
Extremely High (9) | 9 | 27 | 45 | 63 | 81
High (8) | 8 | 24 | 40 R-004 Reputational (Score: 40) | 56 R-001 Financial (Score: 56) | 72 R-003 Competitive (Score: 72)
Somewhat High (6) | 6 | 18 | 30 | 42 R-002 Operational (Score 42) R-002 Operational (Score: 42) R-005 Legal/Compliance (Score: 42) R-006 Operational/Technology (Score: 42)e: 42) | 54
Moderate (4) | 4 | 12 | 20 | 28 | 36
Somewhat Low (2) | 2 | 6 | 10 | 14 | 18
Very Low (1) | 1 | 3 | 5 | 7 | 9
→ X-axis = Likelihood ¦ Y-axis = Impact ¦ Each cell = Likelihood × Impact ¦ Risks plotted at their exact score coordinates.

## Risk Register
AMERICAN EXPRESS EMV TRANSITION — RISK REGISTER
Risk # | Date | The Risk of/That | Caused by | Resulting In | Consequence / Impact | Likelihood Score | Impact Score | Risk Score | Priority (H,M,L) | Mitigation | Risk Owner | Open/Closed
R-001 | Mar 2026 | Card-not-present (CNP) fraud losses increase significantly as EMV reduces card-present fraud | EMV chip eliminating card-present counterfeit fraud, redirecting fraudsters to online and phone-based channels | Increased financial losses on online transactions not protected by chip technology | Significant CNP fraud chargebacks affecting net revenue and fraud-related operational costs | 7 | 8 | 56 | H | Deploy tokenization, 3D Secure authentication, CVV verification; enhance real-time CNP fraud monitoring | Chief Risk Officer | Open
R-002 | Mar 2026 | Merchant EMV terminal certification is delayed due to Amex's closed-loop certification requirements | Amex's proprietary end-to-end terminal certification being more complex than Visa/Mastercard open-loop systems | Merchants exposed to fraud liability during certification gaps; reduced Amex in-person acceptance during transition | Operational disruption and slowed EMV adoption, creating merchant network coverage gaps | 7 | 6 | 42 | M | Streamline certification process; deploy dedicated merchant support teams to accelerate terminal approvals | Chief Operating Officer | Open
R-003 | Mar 2026 | Amex loses merchant acceptance share to Visa and Mastercard during the EMV rollout | Visa and Mastercard's open-loop networks enabling faster, broader terminal upgrades at scale | Cardholders experiencing Amex declines at non-certified merchants, reducing usage and satisfaction | Competitive disadvantage resulting in lost transactions and potential cardholder attrition | 9 | 8 | 72 | H | Leverage Expresspay contactless and Amex Quick Chip to improve acceptance speed; partner with acquirers for faster rollout | Chief Commercial Officer | Open
R-004 | Mar 2026 | Brand damage occurs if fraud incidents during the EMV transition window are publicly reported | Fraud occurring prior to full merchant EMV adoption, damaging trust in Amex's premium brand promise | Erosion of premium brand positioning among high-spending Platinum and Centurion cardholders | Long-term reputational harm, reduced card acquisition, and loss of loyalty from premium cardholders | 5 | 8 | 40 | M | Proactively communicate chip security enhancements; maintain transparent and rapid incident response protocols | Chief Marketing Officer | Open
R- 005 | 2016-03-01 | Amex faces antitrust litigation and legal liability arising from the coordinated EMV liability shift | Merchants alleging that American Express, Visa, Mastercard and Discover conspired to simultaneously shift chargeback liability onto merchants in an anticompetitive manner during the October 2015 EMV rollout | Class action lawsuit (B&R Supermarket v. Visa et al.) resulting in Amex paying a $20 million settlement and ongoing legal costs | Legal: Settlement costs, litigation fees, and regulatory scrutiny. Reputational: Damaged merchant relationships and public perception of Amex as an anticompetitive actor. Financial: Direct settlement payout of $20M plus legal expenses | 7 | 6 | 42 | M | Engage proactively with merchant associations; revise chargeback policies for small transactions; maintain legal reserves for EMV-related litigation; ensure transparent communication of liability shift rules | Chief Legal Officer / General Counsel | Open
R- 006 | 2016 | EMV-certified terminals fail to process Amex chip transactions correctly due to software and compliance deficiencies | Merchants having EMV hardware installed but lacking the correct software configurations or Amex-specific compliance certifications needed to successfully process chip transactions, compounded by the fact that 40% of Amex counterfeit chargebacks were on transactions under $25 | Continued fraud exposure and chargeback losses at technically "certified" merchant locations, undermining the purpose of the EMV transition | Operational: Terminal failures disrupt checkout experiences and erode merchant confidence in Amex. Financial: Ongoing chargeback losses despite hardware upgrades. Technology: Amex's closed-loop certification process unable to catch software-level compliance gaps at scale | 7 | 6 | 42 | M | Deploy Amex-specific software compliance testing tools; provide merchants with end-to-end certification support beyond hardware; implement real-time transaction monitoring to flag terminals with high failure rates | Chief Technology Officer / VP Merchant Operations | Open